## Sheet1
PSP Time Recording Log
Student | Nick Leslie
Program | Number Guessing Game
Instructor | Amit / Luofeng
Project | Phase | Date | Start | Int Time | Stop | Delta Time | Comments
Game Two | Planning | 2019-03-24 | 1:00pm |  | 1:01pm |  | Start planning, project summary
| Design | 2019-04-03 | 2:13pm |  | 2:21pm |  | Preliminary designs
| Testing | 2019-04-03 | 2:23pm |  | 2:32pm |  | Write tests
| Design | 2019-04-03 | 2:37pm |  | 2:40pm |  | More design
| Coding | 2019-04-03 | 3:16pm |  | 3:21pm |  | Code
| Coding | 2019-04-03 | 3:31pm |  | 3:35pm |  | Code
| Coding | 2019-04-03 | 3:42pm |  | 3:48pm |  | Code
| Coding | 2019-04-03 | 4:22pm |  | 4:31pm |  | Code
| Coding | 2019-04-03 | 4:36pm |  | 4:53pm |  | Code
| Coding | 2019-04-03 | 6:55pm |  | 7:05pm |  | Code
| Testing | 2019-04-04 | 10:13am |  | 10:19am |  | Test code
| Coding | 2019-04-04 | 10:46am |  | 10:56am |  | Fix code
| Testing | 2019-04-04 | 10:56am |  | 10:57am |  | Test again
| Design | 2019-04-04 | 11:02am |  | 11:07am |  | Fix designs

## Instructions
Time Recording Log Instructions
General | - Record all of the time you spend on the project.
- Record the time in minutes.
- Be as accurate as possible.
- If you need additional space, use another copy of the form.
- If you forget to record the starting, stopping, or interruption time for an activity, promptly enter your best estimate.
Header | - Enter your name and the date.
- Enter the program name and number.
- Enter the instructor’s name and the programming language you are using.
Project | Enter the program name or number.
Phase | Enter the name of the phase for the activity you worked on, e.g. Planning, Design, Test.
Start Date and Time | Enter the date and time when you start working on a process activity.
Interruption Time | - Record any interruption time that was not spent on the process activity.
- If you have several interruptions, enter their total time.
- You may enter the reason for the interrupt in comments.
Stop Date and Time | Enter the date and time when you stop working on that process activity.
Delta Time | Enter the clock time you actually spent working on the process activity, less the interruption time.
Comments | Enter any other pertinent comments that might later remind you of any unusual circumstances regarding this activity.